## Project Planner
XXXX HVAC WORK
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: |  | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE |  | WEEK
[6 empty] | START | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05 | 2024-07-06 | 2024-07-07 | 2024-07-08 | 2024-07-09 | 2024-07-10 | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | 2024-07-15 | 2024-07-16 | 2024-07-17 | 2024-07-18 | 2024-07-19 | 2024-07-20 | 2024-07-21 | 2024-07-22 | 2024-07-23 | 2024-07-24 | 2024-07-25 | 2024-07-26 | 2024-07-27 | 2024-07-28 | 2024-07-29 | 2024-07-30 | 2024-07-31 | 2024-08-01 | 2024-08-02 | 2024-08-03 | 2024-08-04 | 2024-08-05 | 2024-08-06 | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | 2024-08-11 | 2024-08-12 | 2024-08-13 | 2024-08-14 | 2024-08-15 | 2024-08-16 | 2024-08-17 | 2024-08-18 | 2024-08-19 | 2024-08-20 | 2024-08-21 | 2024-08-22 | 2024-08-23 | 2024-08-24 | 2024-08-25 | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | 2024-08-30 | 2024-08-31 | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-09 | 2024-09-10 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-20 | 2024-09-21 | 2024-09-22 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-10 | 2024-10-11 | 2024-10-12 | 2024-10-13 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-10-18 | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19
[7 empty] | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180
PO RECEIVE | 1 | 1
KICK OFF MEETING | 4 | 1
MEETING WITH PRINCIPAL/OEM | 7 | 1
SITE ASSESSMENT | 16 | 1
ORDER PLACEMENT | 18 | 1
CONTRACT SIGNING | 40 | 1
ADVANCE RECEIVED | 59 | 1
DELIVERY OF LOCAL MATERIALS | 75 | 1
DELIVERY OF STOCK MACHINES | 84 | 2
IMPORT MATERIALS READINESS | 1 | 102
IMPORT MATERIALS SHIPMENT | 103 | 7
IMPORT MATERIALS ARRIVAL AT CTG PORT | 110 | 30
CUSTOMS CELARANCE | 140 | 14
IMPORT MATERIALS DELIVERY AT SITE | 154 | 1
SHOP DRAWING SUBMISSION | 52 | 1
SHOP DRAWING APPROVAL | 70 | 75
SITE ASSESSMENT | 65 | 1
TECHNICAL DISCUSSION | 70 | 1
SITE MOBILIZATION & INDUCTION | 72 | 3
WORK START
KNITTING & MAINT WORKSHOP (ZONE-1) | 75 | 16
CUTTING & MAINTENANCE WORKSHOP (ZONE-2) | 75 | 16
ENGINEERING WORKSHOP GF (ZONE-3) | 91 | 17
PROCUREMENT & HR SECTION GF (ZONE-4) | 91 | 17
CANTEEN & SUBSTATION (ZONE-5) | 108 | 10
PROCUREMENT & HR SECTION MF (ZONE-6) | 114 | 10
SEWING CANTEEN & OFFICE MZ (ZONE-7) | 124 | 15
ELECTRICAL WIRING & POWER AVAILABILITY (ZONE 1~2) | 85 | 1
ELECTRICAL WIRING & POWER AVAILABILITY (ZONE 3) | 85 | 1
ELECTRICAL WIRING & POWER AVAILABILITY (ZONE 4~7) | 104 | 1
TESTING COMMISSIONING (ZONE 1~2) | 92 | 4
TESTING COMMISSIONING (ZONE 3) | 108 | 4
TESTING COMMISSIONING (ZONE 4~7) | 163 | 7

## Project Planner (3)
XXXXX HVAC WORK
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: |  | 2024-06-23 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | PLAN END | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE |  | DAY
[7 empty] | START | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180
[8 empty] | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
 | time axis 2024-06-23 to 2024-12-19
PO RECEIVE | 2024-06-23 | 1 | 2024-06-23
KICK OFF MEETING | 2024-06-26 | 1 | 2024-06-26
MEETING WITH PRINCIPAL/OEM | 2024-06-29 | 1 | 2024-06-29
SITE ASSESSMENT | 2024-07-08 | 1 | 2024-07-08
ORDER PLACEMENT | 2024-07-10 | 1 | 2024-07-10
CONTRACT SIGNING | 2024-08-01 | 1 | 2024-08-01
ADVANCE RECEIVED | 2024-08-20 | 1 | 2024-08-20
DELIVERY OF LOCAL MATERIALS | 2024-09-05 | 1 | 2024-09-05
DELIVERY OF STOCK MACHINES | 2024-09-14 | 2 | 2024-09-15
IMPORT MATERIALS PRODUCTION | 2024-06-23 | 102 | 2024-10-02
IMPORT MATERIALS SHIPMENT | 2024-10-03 | 7 | 2024-10-09
IMPORT MATERIALS ARRIVAL AT CTG PORT | 2024-10-10 | 30 | 2024-11-08
CUSTOMS CELARANCE | 2024-11-09 | 14 | 2024-11-22
IMPORT MATERIALS DELIVERY AT SITE | 2024-11-23 | 1 | 2024-11-23
SHOP DRAWING SUBMISSION | 2024-08-13 | 1 | 2024-08-13
SHOP DRAWING APPROVAL | 2024-08-31 | 75 | 2024-11-13
SITE ASSESSMENT | 2024-08-26 | 1 | 2024-08-26
TECHNICAL DISCUSSION | 2024-08-31 | 1 | 2024-08-31
SITE MOBILIZATION & INDUCTION | 2024-09-02 | 3 | 2024-09-04
WORK START
KNITTING & MAINT WORKSHOP (ZONE-1) | 2024-09-05 | 16 | 2024-09-20
CUTTING & MAINTENANCE WORKSHOP (ZONE-2) | 2024-09-05 | 16 | 2024-09-20
ENGINEERING WORKSHOP GF (ZONE-3) | 2024-09-21 | 17 | 2024-10-07
PROCUREMENT & HR SECTION GF (ZONE-4) | 2024-09-21 | 17 | 2024-10-07
CANTEEN & SUBSTATION (ZONE-5) | 2024-10-08 | 10 | 2024-10-17
PROCUREMENT & HR SECTION MF (ZONE-6) | 2024-10-14 | 10 | 2024-10-23
SEWING CANTEEN & OFFICE MZ (ZONE-7) | 2024-10-24 | 15 | 2024-11-07
ELECTRICAL WIRING & POWER AVAILABILITY (ZONE 1~2) | 2024-09-15 | 1 | 2024-09-15
ELECTRICAL WIRING & POWER AVAILABILITY (ZONE 3) | 2024-09-15 | 1 | 2024-09-15
ELECTRICAL WIRING & POWER AVAILABILITY (ZONE 4~7) | 2024-10-04 | 1 | 2024-10-04
TESTING COMMISSIONING (ZONE 1~2) | 2024-09-22 | 4 | 2024-09-25
TESTING COMMISSIONING (ZONE 3) | 2024-10-08 | 4 | 2024-10-11
TESTING COMMISSIONING (ZONE 4~7) | 2024-12-02 | 7 | 2024-12-08
Formulas:
PLAN END = [PLAN START]+[PLAN DURATION]-1

## Schedule
WORK / ZONE | CEILING/ ACP OPENING |  | MARKING |  | SUPPORT WORK |  | COPPER PIPING |  | PRESSURE TEST-PIPELINE |  | DRAIN PIPE |  | NETWORKING |  | DUCTING |  | MACHINE INSTALLATION |  | PRESSURE TEST-SYSTEM |  | ELECTRICAL CABLE WORK |  | CEILING/ ACP CLOSING |  | AIR TERMINALS INSTALLATION |  | TESTING & COMMISSIONING |  | MACHINE ARRIVAL | 64
| START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | STOCK MACHINE | 10
KNITTING & MAINT WORKSHOP |  | 0 | 1 | 1 | 2 | 3 | 4 | 7 |  |  | 8 | 8 | 9 | 9 | 1 | 6 | 10 | 11 | 12 | 13 |  | 8 | 13 | 20 | 21 | 21 | 14 | 17 | START DATE | 1
CUTTING & MAINTENANCE WORKSHOP |  | 0 | 1 | 1 | 2 | 3 | 4 | 7 |  |  | 8 | 8 | 9 | 9 |  |  | 10 | 11 | 12 | 13 |  | 8 | 13 | 20 |  |  | 14 | 17
ENGINEERING WORKSHOP GF |  | 12 | 13 | 13 | 14 | 17 | 18 | 21 |  |  | 22 | 23 | 24 | 24 | 14 | 18 | 16 | 17 | 22 | 23 |  | 14 | 23 | 30 | 31 | 32 | 24 | 27
PROCUREMENT & HR SECTION GF |  | 12 | 13 | 13 | 14 | 17 | 18 | 22 | 23 | 25 | 23 | 24 | 25 | 25 | 14 | 25 | 65 | 67 | 68 | 69 |  | 63 | 26 | 33 | 34 | 35 | 70 | 73
CANTEEN & SUBSTATION |  | 25 | 26 | 26 | 26 | 27 | 28 | 30 | 31 | 33 | 28 | 30 | 28 | 30 | 19 | 30 | 65 | 67 | 68 | 69 |  | 63 | 34 | 41 | 42 | 43 | 70 | 73
PROCUREMENT & HR SECTION MF |  | 30 | 31 | 31 | 31 | 32 | 33 | 34 | 35 | 37 | 35 | 35 | 36 | 36 | 31 | 36 | 68 | 70 | 71 | 72 |  | 66 | 38 | 45 | 46 | 47 | 73 | 76
SEWING CANTEEN & OFFICE MZ |  | 36 | 37 | 37 | 38 | 42 | 43 | 46 | 47 | 49 | 47 | 48 | 47 | 48 | 37 | 46 | 71 | 74 | 75 | 76 |  | 69 | 50 | 57 | 58 | 59 | 77 | 80
COLOR SERVICE ZONE |  | -1
SPARE PARTS WAREHOUSE |  | -1
CANTEEN & OFFICE |  | -1
SEWING FLOOR |  | -1
Site Assessment | 2024-08-26 | 2024-08-26
Technical Discussion |  | 2024-08-29
Drawing Approval |  | 2024-08-31
Local Material Requisition |  | 2024-08-27
Local Material Delivery |  | 2024-09-01
Ready Stock Machine Delivery |  | 2024-09-14 | 9
Import Machine Delivery |  | 2024-11-23 | 79
Site Mobilization |  | 2024-09-01
Induction |  | 2024-09-03
Start |  | 2024-09-05

## DATE
WORK / ZONE | CEILING/ ACP OPENING |  | MARKING |  | SUPPORT WORK |  | COPPER PIPING |  | PRESSURE TEST-PIPELINE |  | DRAIN PIPE |  | NETWORKING |  | DUCTING |  | MACHINE INSTALLATION |  | PRESSURE TEST-SYSTEM |  | ELECTRICAL CABLE WORK |  | CEILING/ ACP CLOSING |  | AIR TERMINALS INSTALLATION |  | TESTING & COMMISSIONING |  | MACHINE ARRIVAL | 2024-11-23
| START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | STOCK MACHINE | 2024-09-14
KNITTING & MAINT WORKSHOP |  | 2024-09-04 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-11 |  |  | 2024-09-12 | 2024-09-12 | 2024-09-13 | 2024-09-13 | 2024-09-05 | 2024-09-10 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 |  | 2024-09-12 | 2024-09-17 | 2024-09-24 | 2024-09-25 | 2024-09-25 | 2024-09-18 | 2024-09-21 | START DATE | 2024-09-05
CUTTING & MAINTENANCE WORKSHOP |  | 2024-09-04 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-11 |  |  | 2024-09-12 | 2024-09-12 | 2024-09-13 | 2024-09-13 |  |  | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 |  | 2024-09-12 | 2024-09-17 | 2024-09-24 |  |  | 2024-09-18 | 2024-09-21
ENGINEERING WORKSHOP GF |  | 2024-09-16 | 2024-09-17 | 2024-09-17 | 2024-09-18 | 2024-09-21 | 2024-09-22 | 2024-09-25 |  |  | 2024-09-26 | 2024-09-27 | 2024-09-28 | 2024-09-28 | 2024-09-18 | 2024-09-22 | 2024-09-20 | 2024-09-21 | 2024-09-26 | 2024-09-27 |  | 2024-09-18 | 2024-09-27 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-09-28 | 2024-10-01
PROCUREMENT & HR SECTION GF |  | 2024-09-16 | 2024-09-17 | 2024-09-17 | 2024-09-18 | 2024-09-21 | 2024-09-22 | 2024-09-26 | 2024-09-27 | 2024-09-29 | 2024-09-27 | 2024-09-28 | 2024-09-29 | 2024-09-29 | 2024-09-18 | 2024-09-29 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-28 |  | 2024-11-22 | 2024-09-30 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-11-29 | 2024-12-02
CANTEEN & SUBSTATION |  | 2024-09-29 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-10-01 | 2024-10-02 | 2024-10-04 | 2024-10-05 | 2024-10-07 | 2024-10-02 | 2024-10-04 | 2024-10-02 | 2024-10-04 | 2024-09-23 | 2024-10-04 | 2024-11-24 | 2024-11-26 | 2024-11-27 | 2024-11-28 |  | 2024-11-22 | 2024-10-08 | 2024-10-15 | 2024-10-16 | 2024-10-17 | 2024-11-29 | 2024-12-02
PROCUREMENT & HR SECTION MF |  | 2024-10-04 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-06 | 2024-10-07 | 2024-10-08 | 2024-10-09 | 2024-10-11 | 2024-10-09 | 2024-10-09 | 2024-10-10 | 2024-10-10 | 2024-10-05 | 2024-10-10 | 2024-11-27 | 2024-11-29 | 2024-11-30 | 2024-12-01 |  | 2024-11-25 | 2024-10-12 | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-12-02 | 2024-12-05
SEWING CANTEEN & OFFICE MZ |  | 2024-10-10 | 2024-10-11 | 2024-10-11 | 2024-10-12 | 2024-10-16 | 2024-10-17 | 2024-10-20 | 2024-10-21 | 2024-10-23 | 2024-10-21 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-11 | 2024-10-20 | 2024-11-30 | 2024-12-03 | 2024-12-04 | 2024-12-05 |  | 2024-11-28 | 2024-10-24 | 2024-10-31 | 2024-11-01 | 2024-11-02 | 2024-12-06 | 2024-12-09
COLOR SERVICE ZONE
SPARE PARTS WAREHOUSE
CANTEEN & OFFICE
SEWING FLOOR
COMMISSIONING
Site Assessment | 2024-08-26 | 2024-08-26 |  |  |  |  | 2024-09-05 | 2024-09-16 | 2024-09-21 | 2024-09-25 | 2024-09-05 | 2024-09-20 | 15 | 11 | 75
Technical Discussion |  | 2024-08-29 |  |  |  |  | 2024-09-05 | 2024-09-16 | 2024-09-21 | 2024-09-25 | 2024-09-05 | 2024-09-20 | 15 | 11 | 75
Drawing Approval |  | 2024-08-31 |  |  |  |  | 2024-09-17 | 2024-09-27 | 2024-10-01 | 2024-10-05 | 2024-09-21 | 2024-10-07 | 16 | 10 | 91
Local Material Requisition |  | 2024-08-27 |  |  |  |  | 2024-09-17 | 2024-09-27 | 2024-12-02 | 2024-12-06 | 2024-09-21 | 2024-10-07 | 16 | 10 | 91
Local Material Delivery |  | 2024-09-01 |  |  |  |  | 2024-09-29 | 2024-10-04 | 2024-12-02 | 2024-12-06 | 2024-10-08 | 2024-10-17 | 9 | 5 | 108
Ready Stock Machine Delivery |  | 2024-09-14 | 9 |  |  |  | 2024-10-05 | 2024-10-10 | 2024-12-05 |  | 2024-10-14 | 2024-10-23 | 9 | 5 | 114
Import Machine Delivery |  | 2024-11-23 | 79 |  |  |  | 2024-10-11 | 2024-10-22 | 2024-12-09 |  | 2024-10-24 | 2024-11-07 | 14 | 11 | 124
Site Mobilization |  | 2024-09-01
Induction |  | 2024-09-03 | [10 empty] | 63
Start |  | 2024-09-05

## SCOPE
Client | Flash back??
Ceiling Opening | Oxygen trolley
ACP Opening | Acetylene trolley
Roof Core Cutting | Fire Blanket
Ceiling Frame Cutting | Scaffolding
Crane for Outdoor Lifting | platform
Apron
Safety belt
Leather hand gloves
Normal hand gloves
Air fresh??? helmet
Ark welding helmet
Wheel for scaffolding
Helmet
Fire extinguisher
Industrial plug
Industrial soket
Sunglass
Black sunglasses for welding
Safety shoe
Double hook safety belt
***"Oxygen,,,, cetylene,,,,nitrogen.. From linde"

## Project Planner (2)
XXXX HVAC WORK
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127
 | time axis 2024-08-27 to 2024-12-31
Local Materials Requisition | 2024-08-27 | 1
Work Order Issue | 2024-08-30 | 1
Local Material Purchase 70% | 2024-09-05 | 1
Copper Pipes | 2024-09-05 | 1
Insulation | 2024-09-05 | 1
Cables | 2024-09-05 | 1
Refrigerant Gas | 2024-09-05 | 1
Drain Pipes | 2024-09-05 | 1
Tools | 2024-08-30 | 1
Uniforms | 2024-08-30 | 1
House Rent | 2024-08-30 | 1
Man Power Hiring | 2024-09-02 | 1
Ducting Vendor Selection | 2024-08-30 | 1
Safety Officer Appointment
Drawing Approval
INDUCTION
WORK START
CEILING OPENING
MARKING
SUPPORT WORK
COPPER PIPE WORK
PIPELINE PRESSURE TESTING
DRAIN PIPE WORK
NETWORKING
DUCTING
MACHINE INSTALLATION
SYSTEM PRESSURE TESTING
ELECTRICAL CABLE WORK
CEILING/ACP CLOSING
AIR TERMINALS INSTALLATION
TESTING & COMMISSIONING
HANDOVER

## TOOLS
PROJECT REQUISITION
XXXXXXXX
for Internal Use Only
Project Name: XXXXXXX |  | DATE: 27 Aug 2024
Purpose: Safety Gear and Tools |  | Prepared By:
XXXX SAFETY GEARS AND TOOLS REQUIREMENTS
Sl No | Description | Image | Qty | Unit | Remarks
1 | Retractable Badge Holder for Face ID |  | 30 | pcs | Fresco + N.A Engg
2 | Face ID for New Employees |  | 16 | pcs | Fresco + N.A Engg
3 | Safety Vest (With Logo) |  | 50 | pcs | Fresco + N.A Engg
4 | Helmet (With Logo) |  | 22 | pcs | Fresco
5 | Steel Toe Safety Shoe |  | 22 | pcs | 10 Tech+ 2 Supervisor+ 1 Safety Officer+ 1 Shiraj+ 1 Arif+ 1 Humayra+ 1 MD Sir
6 | Hand Gloves |  | 50 | pcs | Fresco
7 | Clear Lens Safety Glasses |  | 20 | pcs | Fresco
8 | Shade Lens Safety Glasses (for Gas Welding) |  | 10 | pcs | Fresco
9 | Ear Plugs |  | 30 | pcs | Fresco
10 | Face Sheild/ Safety Sheild (clear) |  | 6 | pcs | Fresco
11 | Leather Welding Apron (full Sleeve) |  | 3 | pcs | Fresco
12 | Leather Hand Gloves for Welders |  | 4 | pcs | Fresco
13 | Arc Welding Helmet |  | 3 | pcs | Fresco
14 | Double Hook Body Harness |  | 6 | pcs | Fresco
15 | Flashback Arrestor for Oxygen Acetylene |  | 12 | pcs | Fresco
16 | Industrial Plug |  | 12 | pcs | Fresco
17 | Industrial Socket |  | 12 | pcs | Fresco
18 | Welding Ground Earth Clamp Kit - 500Amps |  | 1 | Pcs | Fresco
19 | Welding machine Earth Clamp Connector |  | 2 | Pcs | Fresco
20 | Service Cable 3Corex2.5rm |  | 2 | coil | Fresco
21 | Gas Cylinder Trolley (Single) |  | 2 | pcs | Fresco
22 | Gas Cylinder Trolley (Double) |  | 2 | pcs | Fresco
23 | Fire Extinguisher (Dry Powder & CO2) |  | 2 | set | Fresco
24 | Fire Blanket |  | 10 | pcs | Fresco
25 | Caution Tape |  | 30 | Pcs | Fresco
26 | Foldable Trolley |  | 2 | Pcs | Fresco
27 | Traffic Cones |  | 8 | Pcs | Fresco
28 | Scaffolding Wheel - 4" |  | 8 | Pcs | Fresco
29 | Scaffolding |  | 8 | Pcs | Fresco
30 | Scaffolding Pipe 2" - (Length - 20 Rft) |  | 20 | Pcs | Fresco
31 | Scaffolding Clamp |  | 100 | Pcs | Fresco
32 | scaffolding steel plank |  | 10 | Pcs | Fresco
33 | Oxygen, Acetylene Meter |  | 3 | Pcs | Fresco
34 | Bench Drille |  | 1 | Pcs | Fresco
35 | Trunk |  | 1 | Pcs | Fresco
36 | Tool-(Custom Made) |  | 4 | Pcs | Fresco

## Schedule (2) (hidden)
WORK / ZONE | CEILING/ ACP OPENING |  | MARKING |  | SUPPORT WORK |  | COPPER PIPING |  | PRESSURE TESTING-1 |  | DRAIN PIPE |  | NETWORKING |  | DUCTING |  | MACHINE INSTALLATION |  | PRESSURE TESTING-2 |  | ELECTRICAL CABLE WORK |  | CEILING/ ACP CLOSING |  | AIR TERMINALS INSTALLATION |  | TESTING & COMMISSIONING |  | MACHINE ARRIVAL | 70
| START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | START | END | STOCK MACHINE | 20
KNITTING & MAINT WORKSHOP |  | 0 | 1 | 1 | 2 | 3 | 4 | 7 | 8 | 10 | 8 | 8 | 9 | 9 | 1 | 6 | 24 | 25 | 26 | 27 |  | 22 | 11 | 18 | 19 | 19 | 28 | 31 | START DATE | 1
CUTTING & MAINTENANCE WORKSHOP |  | 0 | 1 | 1 | 2 | 3 | 4 | 7 | 8 | 10 | 8 | 8 | 9 | 9 |  |  | 24 | 25 | 26 | 27 |  | 22 | 11 | 18 |  |  | 28 | 31
ENGINEERING WORKSHOP GF |  | 9 | 10 | 10 | 11 | 13 | 14 | 17 |  |  | 18 | 19 | 20 | 20 | 11 | 15 | 21 | 22 | 23 | 24 |  | 19 | 1 | 8 | 9 | 10 | 25 | 28
PROCUREMENT & HR SECTION GF |  | 9 | 10 | 10 | 11 | 14 | 15 | 19 | 20 | 22 | 20 | 21 | 22 | 22 | 11 | 22 | 71 | 73 | 74 | 75 |  | 69 | 23 | 30 | 31 | 32 | 76 | 79
CANTEEN & SUBSTATION |  | 26 | 27 | 27 | 27 | 28 | 29 | 31 | 32 | 34 | 29 | 31 | 29 | 31 | 16 | 31 | 71 | 73 | 74 | 75 |  | 69 | 35 | 42 | 43 | 44 | 76 | 79
PROCUREMENT & HR SECTION MF |  | 31 | 32 | 32 | 32 | 33 | 34 | 35 | 36 | 38 | 36 | 36 | 37 | 37 | 32 | 37 | 74 | 76 | 77 | 78 |  | 72 | 39 | 46 | 47 | 48 | 79 | 82
SEWING CANTEEN & OFFICE MZ |  | 37 | 38 | 38 | 39 | 43 | 44 | 47 | 48 | 50 | 48 | 49 | 48 | 49 | 38 | 47 | 77 | 80 | 81 | 82 |  | 75 | 51 | 58 | 59 | 60 | 83 | 86
COLOR SERVICE ZONE |  | -1
SPARE PARTS WAREHOUSE |  | -1
CANTEEN & OFFICE |  | -1
SEWING FLOOR |  | -1
Site Assessment | 2024-08-26 | 2024-08-27
Technical Discussion |  | 2024-08-29
Drawing Approval |  | 2024-08-31
Local Material Requisition |  | 2024-08-25
Local Material Delivery |  | 2024-09-01
Ready Stock Machine Delivery |  | 2024-09-14
Import Machine Delivery |  | 2024-12-15 | 110
Site Mobilization |  | 2024-09-01
Induction |  | 2024-09-03
Start |  | 2024-09-04
Formulas:
END = [END, row above]+2